## Dash
Asset ID / Location | Date | Road Name | Defect Severity (Grade) | Defect Length (m) | Damage Description | Total Length (m) | Recommended Action | Estimated Cost - Epoxy (£) | Estimated Cost - iFlex (£) | Savings | Actual Cost | Cost Variance | Installation Time - Epoxy (hrs) | Installation Time - iFlex (hrs) | Excavation Needed (Y/N) | Time Saved | Actual Time | Time Variance | Site Difficulty Level (Low/Med/High) | Notes | Status
GY-1355 | 2025-07-01 | Albert Road | High (STR Grade 4.0) | 4.6m to 7.7m | Multiple cracks + encrustation | 12.99 | Full sleeve | 18797.147 | 1085.0547 | 17712.0923 | 860 | 225.0547 | 13 | 1.732 | No | 11.268 | 1.2 | 0.532 | low | n/a | Open | Epoxy rate | 580.96
GY-1361 | 2025-07-02 | Albert Road | Grade 4 (multiple) | 2.24m to 2.67m | Pipe holes and breaks pose risk of collapse, infiltration | 3.32 | Full sleeve, despite severe defects (holes, fractures, broken pipe), the pipe retains continuous structure with no collapse, allowing a liner to form a new watertight pipe within, is faster, cheaper and restores structural integrity. A pre-lining CCTV survey is recommended to verify the current status of all previously identified defects and ensure suitability for full-length relining | 4804.1977 | 277.3196 | 4526.8781 | 204 | 73.3196 | 3.32 | 0.44267 | No | 2.8773 | 0.3 | 0.14267 | low | n/a | Open | Iflex rate | 83.53
GY-12241 | 2025-07-03 | Albert Road | Grade 3 (Structural), Grade 2 (Roots) | 2.58m to 3.29m | Multiple longitudinal fractures and root ingress | 8.82 | Although the pipe has moderate longitudinal fractures and minor root ingress, the structure remains intact with no collapse or major deformation. Recommend lining since the structure intact on re-survey | 12762.959 | 736.7346 | 12026.2244 | 650 | 86.7346 | 8.82 | 1.176 | No | 7.644 | 1.1 | 0.076 | low | n/a | Open